## Agile Project Backlog
Agile Product Backlog
PROJECT DESCRIPTION
An e-Commerce site where users can shop for sporty shoes. Admin can login to manage the products in the store, including categorizing themKitchen Story is an e-commerce portal that lets people shop food items online. User can select any food item and order it through a dummy payment gateway by logging into the site. Admin has the right to add and remove food-items, can view users and their orders. and can browse the list of users who have signed up and be able to search for users. Moreover, admin can see purchase reports filtered by date and category.
PROJECT BACKLOG
ID | As a | I want to | So that | Priority | Story point | Sprint Assignment | Status
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | User | Have a home page | I can see the different options to choose | Must |  |  | Done
2 | User | Have an option to Login | I can log into the application | Must |  |  | Done
3 | User | Have an option to Sign Up | I can register myself in the appliation | Must |  |  | Done
4 | User | Have an option to change password before login | I can change the password wihout logging in | Must |  |  | Done
5 | User | Have an option search for dishes | I can search for any dish that is avaliable | Must |  |  | Done
6 | User | Have an option to view menu | I can see the list of dishes avaliable to order | Must |  |  | Done
7 | User | Have an option to view dish | I can see the detail of the dish and add to cart | Must |  |  | Done
8 | User | Have an option to add a dish to cart | I can add the dish to cart | Must |  |  | Done
9 | User | Have an option to view cart | I can see the list of dishes in the cart | Must |  |  | Done
10 | User | Have an option to order dishes | I can order dishes which are in the cart | Must |  |  | Done
11 | User | View the order status | I can see the details of order and order status | Must |  |  | Done
12 | User | Have an option to view all my orders | I can see the history of my orders | Must |  |  | Done
13 | User | Have an option to view my profile | I can see my profile details | Must |  |  | Done
14 | User | Have an option to change password | I can change the password | Must |  |  | Done
15 | Admin | Have an option to add a dish to inventory | I can add a dish to inventory | Must |  |  | Done
16 | Admin | Have an option to view all dishes | I can see all the dishes in the inventory | Must |  |  | Done
17 | Admin | Have an option to edit a dish | I can update the details of the dish | Must |  |  | Done
18 | Admin | Have an option to delete a dish | I can delete a dish from inventory | Must |  |  | Done
19 | Admin | Have an option to view all Users | I can see all users who are registered in the application | Must |  |  | Done
20 | Admin | Have an option to view all orders | I can see the orders of all users | Must |  |  | Done
21 | Admin | Have an option to view an order | I can see the order of a user | Must |  |  | Done
22 | Admin | Have an option to update user details | I can update the details of the user | Must |  |  | Done
23 | Admin | Have an error page | User can find out what went wrong | Must |  |  | Done
24 | User | Have an option to logout | I can logout | Must |  |  | Done

## Agile Sprint Backlog
Agile Sprint Backlog
SUMMARY
CHANGE IN SCOPE
| Original Story Points |  | 573
| New Points |  | .
| Total Points |  | 573
| CHANGE IN SCOPE |  | 0%
SPRINT BACKLOG
ID | Backlog task | Assigned to | Story points | New points? | Release | Status | Business value | Change management notes | Initial estimate
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours
1 | As an user I should have a home page
1.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.4 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.5 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
2 | As an user I should have an option to login, so that I can login
2.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
2.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
3 | As an user, I should have an option to change password before login, so that I can change the password
3.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
3.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
4 | As a User, I should have an option to signup, so that I can register my details in the application
4.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
4.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
5 | As an User, I should have an option to search for a dish, so that I can search for any dish
5.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
5.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
6 | As an User, I should have an option to view menu, so that I can view the menu of dishes
6.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
6.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
7 | As an User, I should have an option to view dish, so that I can see the details of the dish
7.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
7.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
8 | As an User, I should have an option to add a dish to cart, so that I can add the dish to cart
8.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
8.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
9 | As an User, I should have an option to view the cart, so that I can view the dishes in the cart
9.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
9.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
10 | As an User, I should have an option to order dishes, so that I can order dishes in my cart
10.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
10.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
11 | As an User, I should have an option to view all my orders, so that I can view the details of my order
11.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
11.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
11.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
11.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
11.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
11.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
12 | As an User, I should have an option to view my profile, so that I can see my profile details
12.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
12.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
12.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
12.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
12.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
12.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
13 | As an User, I should have an option to change password, so that I can change the password
13.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
13.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
13.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
13.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
13.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
13.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
14 | As an Admin, I should have an option to add a dish, so that I can add a dish to inventory
14.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
14.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
14.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
14.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
14.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
14.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
15 | As an Admin, I should have an option to edit a dish, so that I can update the details of the dish
15.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
15.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
15.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
15.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
15.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
15.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
16 | As an Admin, I should have an option to delete a dish, so that I can delete a dish from inventory
16.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
16.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
16.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
16.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
16.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
16.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
17 | As an Admin, I should have an option to see all dishes, so that I can see the list of dishes present in the inventory
17.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
17.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
17.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
17.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
17.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
17.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
18 | As an Admin, I should haave an option to view all users, so that I can view the list of user who registered in the application
18.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
18.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
18.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
18.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
18.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
18.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
19 | As an Admin, I should have an option to view all orders of users, so that I can view the list of orders of different users
19.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
19.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
19.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
19.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
19.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
19.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
20 | As an Admin, I should have an option to edit user, so that I can update the details of the user
20.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
20.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
20.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
20.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
20.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
20.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
21 | As an Admin, I should have a error page, so that users can find out what went wrong
21.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
21.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
21.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
21.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
21.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
21.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
22 | As a User, I should have an option to logout, so that I can logout of the application
22.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
22.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
22.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
22.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
22.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
22.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0